## Sheet1
RFP Sr. No. | Project Title | Project Owner | Description | Complied No/Partial/Can Be) | Project (Cater's to) | Estimate (In days) | Status (WIP/Planned) | Resource | Planned Date (Start date) | End Date | Note | Why it cannot be completed / why it takes more time | Tech Stack
All SNs | UEBA | Aditya Umathe | All serial numbers depend on this. Redeploy the engine on the OPTCL host and reconnect the SIEM event feed. | Partial | UEBA | 3 | Planned | Aditya | 2026-11-02 | 2026-11-06 | P1 - Platform redeploy and SIEM feed reconnect. By 31-Jan-2027: the engine redeployed on the OPTCL host and the event feed reconnected. This is scheduled first because it starts the 3-7 day behaviour-learning clock that every detection requirement depends on. Full estimate 3 d; all done by 31-Jan-2027. |  | UEBA - complete product (Aditya Umathe, 27-Oct-2026): - Engine: Python 3.12 (3.10 minimum), long-running process in a virtualenv; systemd units ueba-engine, ueba-dashboard, ueba-bridge and a 2-minute watchdog timer; not containerised - Machine learning (CPU only): scikit-learn Isolation Forest, PyTorch autoencoder per entity, hdbscan clustering, faiss-cpu similarity search, numpy, joblib, h5py (versions declared as ranges, not yet pinned) - Storage: SQLite (identity/sessions and behaviour baselines), append-only JSONL alerts, HDF5 training features, FAISS index; archive as zipped JSONL; all local to the UEBA host - Web console: vanilla JavaScript (ES modules, built with Vite 5.4), canvas/SVG charts, globe.gl 3D map; Flask 3 API with flask-cors (52 REST endpoints and a live event stream) - Sign-in: SSO token from the SIEM (JWT HS256) mapped to roles; local accounts in SQLite with scrypt and lockout; roles viewer / analyst / admin - SIEM feed: gzipped JSONL files pulled from the SOC host over SSH by the bridge service (no Kafka or API today) - Notifications and reports: smtplib e-mail, webhooks (urllib), reportlab PDF, openpyxl Excel; XML/CSV/JSON/HTML - Deployment: Ubuntu 22.04 / 24.04, plain install by install_ueba.sh (8 stages, dry-run mode); cron for log rotation and weekly retrain; no message queue, no reverse proxy today; minimum 48 GB RAM, about 500 GB data disk
All SNs | UEBA | Aditya Umathe | All serial numbers depend on this. Automated regression tests across the detection pipeline, console API and identity layer. | Partial | UEBA | 6 | Planned | Aditya | 2026-11-16 | 2027-01-01 | P1 - Automated regression test suite. By 31-Jan-2027: an automated test suite covering the detection pipeline, the console API and the identity layer, run on every change. There is no automated test coverage today, so this protects the other 28 items on this sheet from regression during a compressed build. Full estimate 6 d; all done by 31-Jan-2027.
58 | UEBA | Aditya Umathe | SN 58: The solution's UI should provide a Google-like search bar to search a device by Hostname, Mac Address, Username of user logged into that device, IP Address, Nickname. | Complied - DONE (MAC not buildable) | UEBA | 0 | Done | Aishwarya | 2026-11-02 | 2026-11-06 | DONE. Search by hostname, username, IP address and operator-given nickname all work. MAC address search is NOT buildable: MAC does not appear anywhere in the data the SIEM forwards - zero occurrences in sampling - so there is no field to index. Blocked on the data source, not on effort. Needs MAC-carrying events or an asset register to join against. | PARTIAL - ONE OF THE FIVE SEARCH FIELDS IS NOT BUILDABLE. Hostname, username, IP address and nickname search all work, with nickname added in week 1. MAC address search does not, because MAC does not appear anywhere in the data the SIEM forwards - zero occurrences in a 3,412-event sample - so there is no field to index. Blocked on the data source, not on effort: needs MAC added to the forwarded events, or an asset register to join against.
54, 47 | UEBA | Aditya Umathe | SN 54: The solution's UI should allow displaying threat by user, device and model with sorting and selected period | Complied - DONE 2026 | UEBA | 0 | Done | Aditya | 2026-11-02 | 2026-11-06 | DONE. SN 54: the console displays and sorts threats by user, device and scoring model over any selected period, including which model scored each alert. SN 47: first use of an account, and an account that went quiet and came back, are both raised as named reasons on the alert.
SN 47: Should identify Account used for the first time in a long time
10, 64 | UEBA | Aditya Umathe | SN 10: Integration with enterprise authentication/SSO platforms for simplified access | Complied - DONE 29-Oct-2026 | UEBA | 0 | Done | Aditya | 2026-11-02 | 2026-11-06 | DONE 29-Oct-2026. SN 10: SSO was written but unreachable - the shared secret had never been set, so the dashboard reported sso ready=false and nothing could use it. Secret generated on the host into the service environment file (mode 600, never in source or config) and the exchange exercised end to end against the running dashboard: 19 checks covering role mapping, strongest-group-wins, assertion replay, forged signature, wrong issuer, wrong audience, expiry, stale assertions, alg=none and cookie flags. All pass. SN 64: on-premises lockdown. The product had two outbound paths and both were opt-OUT - the external AI-analyst helper defaulted to enabled, and notification webhooks accepted any URL. Both now pass through one deny-by-default egress gate; a fresh install keeps all customer data on premises and the Audit & Compliance report states the posture from the gate that enforces it. | RESOLVED 29-Oct-2026 - no longer at risk. The earlier note said login enforcement was built but switched off pending the SIEM team's signing inputs. The shared-secret (HS256) path needs none of those: the secret was generated on the production host, SSO now reports ready=true with enforcement ON, and the exchange was verified end to end with 19 checks. The RS256/JWKS path is still available if the SIEM team later prefers it, but it is no longer required for SN 10.
SN 64: The entire Event, Alerts and other information pertaining to Organization's SOC must remain within Organization premises only. Any information moving out of Organization premises shall be reviewed and approved by Organization on need basis.
3 | UEBA | Aditya Umathe | SN 3: Said UEBA tool should be able to integrate with proposed SOAR & SIEM solution and should be from same OEM for monitoring user endpoints and reporting anomalies | Can Be | UEBA | 10 | Planned | Aditya | 2026-11-23 | 2026-12-11 | P1 - SIEM and SOAR integration. By 31-Jan-2027: alerts and incidents pushed out to SOAR on the existing dispatcher, inbound playbook callbacks accepted and authenticated, and state kept in step both ways. Needs the same-OEM decision from the bid lead by Day 10 (12-Nov-2026) and the SOAR API contract and authentication model by Day 25 (26-Nov-2026); if the contract is late the whole 10 d drops out. Full estimate 10 d; all done by 31-Jan-2027. | AT RISK ON TWO EXTERNAL INPUTS, AND A LARGE ITEM (10 d). Needs the same-OEM decision from the bid lead by Day 10 (12-Nov-2026) and the SOAR API contract and authentication model by Day 25 (26-Nov-2026). If the contract is late the full 10 days drops out of the window. The 10 days are large because the integration runs both ways: outbound alert and incident push, inbound playbook callbacks with authentication, and state kept in step between the two.
66 | UEBA | Aditya Umathe | SN 66: Platform should be able to create profiles and monitor all Users in AD from day 1. | No | UEBA | 4 | Planned (partial only) | Aditya | 2026-11-23 | 2026-11-27 | P1 - Active Directory user import. By 31-Jan-2027: every Active Directory user imported, registered and monitored from day one, so no user is invisible. The 'profiles from day 1' wording cannot be met by any UEBA product: a behaviour profile is learned from observed activity and needs 3-7 days of events before it can score anything. Profiles mature over the week after import. Needs Active Directory read access from OPTCL IT by Day 15 (16-Nov-2026). Full estimate 4 d; left after 31-Jan: nothing buildable - the day-1 profile itself is not achievable at any point. | CANNOT BE DONE AT ALL. A behaviour profile is learned from observed activity and needs 3-7 days of events before it can score anything, so no UEBA product can profile users on day one - this is how behavioural analytics works, not a gap in our build. What is delivered instead: every Active Directory user imported, registered and monitored from day one (week 4), so no user is invisible, with profiles maturing over the following week. Also needs AD read access from OPTCL IT by Day 15 (16-Nov-2026).
28 | UEBA | Aditya Umathe | SN 28: The solution should allow network data ingestion from log collectors for Netflows to provide Network Anomaly Detections | Can Be | UEBA | 12 | Planned | Aditya, Aishwarya | 2027-01-18 | 2027-01-29 | P3 - NetFlow ingestion and network anomaly detection. By 31-Jan-2027: network flow records ingested from the log collectors, flow features added to the model, and network anomaly detections raised. Needs confirmation from the OPTCL network team by Day 15 (16-Nov-2026) that NetFlow is collected and where a collector sits; if it is not collected the full 12 d drops out. Full estimate 12 d; all done by 31-Jan-2027. | AT RISK ON THE OPTCL NETWORK TEAM (12 d). Needs confirmation by Day 15 (16-Nov-2026) that NetFlow is collected and where a collector sits. If it is not collected the full 12 days drops out. The 12 days are large because flow records are a new data type for the platform: ingestion from the collectors, new flow features added to the model, and network anomaly detection built on top of them.
5 | UEBA | Aditya Umathe | SN 5: The solution must be able to adjust itself in DHCP environment and yet uniquely identify machines with high accuracy despite change of IP Address | Can Be | UEBA | 4 | Planned | Aditya | 2026-11-23 | 2026-11-27 | P1 - DHCP-safe machine identity. By 31-Jan-2027: machines keep one stable identity across DHCP address changes, by joining events to an asset register or MAC source rather than to the address. Needs the asset registry or a MAC source from OPTCL IT by Day 20 (21-Nov-2026); if that is late, a machine takes a new identity each time its address changes and its baseline restarts. Full estimate 4 d; all done by 31-Jan-2027. | AT RISK ON OPTCL IT. Needs the asset registry, or any source of MAC addresses, by Day 20 (21-Nov-2026). Without one, a machine takes a new identity every time its DHCP address changes and its behaviour baseline restarts from zero, which is the very failure the requirement is written against. The build itself is only 4 days - the input is the constraint, not the effort.
20 | UEBA | Aditya Umathe | SN 20: Use of supervised machine learning algorithms | Can Be | UEBA | 16 | Planned | Aditya, Aishwarya | 2027-01-11 | 2027-01-22 | P3 - Supervised machine learning. By 31-Jan-2027: a supervised training pipeline alongside the existing unsupervised models, with labelling workflow, model governance, accuracy reporting and drift monitoring. Needs a labelled incident dataset - past incidents with analyst verdicts - from the OPTCL SOC by Day 20 (21-Nov-2026). Supervised learning cannot be built without labels, so if the dataset does not arrive the full 16 d drops out. Full estimate 16 d; all done by 31-Jan-2027. | AT RISK - CANNOT BE BUILT AT ALL WITHOUT DATA FROM OPTCL, AND THE SECOND LARGEST ITEM (16 d). Supervised learning needs labels: a dataset of past incidents carrying analyst verdicts, from the OPTCL SOC by Day 20 (21-Nov-2026). With no labels there is no supervised model and the full 16 days drops out. The 16 days cover a training pipeline, a labelling workflow, model governance, accuracy reporting and drift monitoring, all running alongside the existing unsupervised models rather than replacing them.
18 | UEBA | Aditya Umathe | SN 18: Uses self-learning behavioural analysis to dynamically model each device, probabilistically identifying any anomalous activity that falls outside of the device's normal pattern of life. | Can Be | UEBA | 2 | Planned | Aditya | 2026-11-09 | 2026-11-13 | P1 - Behaviour model coverage for sparse and quiet entities. SN 48 is DONE (29-Oct-2026): confirmed-incident history shipped. An analyst can now record that an alert was genuinely malicious - previously only the false-positive verdict existed - and a user or device with that history stays flagged and carries a scoring prior on every later event. SN 18 remains. Measured 29-Oct-2026: 453 personal behaviour models against 996 entities meeting the 2,000-event training bar, and 96.5% of alerts are scored by the shared global model. Raising coverage needs peer-group (cohort) models, and those must come AFTER the identity consolidation retrain: 137,987 of today's entities are largely duplicate identities for the same people, so cohorts built now would be drawn over a fragmented entity space. Sequenced behind the retrain for that reason. Estimate 2 d.
SN 48: Should identify User involved in previously malicious or threatening behaviour
15 | UEBA | Aditya Umathe | SN 15: High privilege access anomaly detection for misuse, sharing, or takeover | Complied - DONE 29-Oct-2026 | UEBA | 0 | Done | Aditya, Aishwarya | 2026-11-09 | 2026-11-13 | DONE 29-Oct-2026, ahead of the 09-Nov start. Privilege is now scored as an entity attribute, so an administrator's unusual behaviour surfaces sooner than a standard user's. Three named behaviours are detected: TAKEOVER (a privileged account on a host it has never used), CREDENTIAL SHARING (one human privileged account across several hosts) and MISUSE (a privileged operation outside business hours). The SOC declares its own privileged accounts from the console and that declaration overrides anything the system infers; where nothing is declared, the level is taken from observed privileged operations and then from the account-name shape, and every verdict records which signal produced it. Machine and service accounts are exempt from the sharing check because being on every host is their job. On this estate that is the difference between a usable signal and three permanent false alarms: SYSTEM is on 12 hosts, NETWORK SERVICE on 11, LOCAL SERVICE on 6. 27 entities classified on the live estate. | NOTE ON SCOPE. Group membership would be the ideal source of privilege and is not forwarded by the SIEM - the same data gap that blocks SN 43 - so there is no 'Domain Admins' membership to read. The serial is met without it, from three other signals, with the SOC's own declaration taking precedence. If account-management events are forwarded later, group membership becomes a fourth and stronger signal with no redesign.
SN 19: Unusual Credential use - models the times and devices normally used by each username, and alerts when there is an unusual combination
17, 40 | UEBA | Aditya Umathe | SN 17: Identifying Trusted Host and Entity Compromise instances | Complied - DONE 30-Oct-2026 | UEBA | 0 | Done | Aditya, Aishwarya | 2026-11-16 | 2026-11-20 | DONE 30-Oct-2026, ahead of the 16-Nov start. One operator register serves both serials: an entity is tagged with a role and a value tier, and the tag changes how its events score. SN 17 - a host declared TRUSTED is held to a HIGHER standard, not a lower one: trust means the host is load-bearing, so anomalous behaviour on it is reported as a possible compromise. SN 40 - access to a tagged high-value asset is measured against what that entity normally does with that asset, so a surge is relative to its own rate rather than an absolute number. First-ever access is reported separately. | SCOPE NOTE. Frequency of access is fully supported (host.name on 100% of events, destination on 97%). FILE-LEVEL download tracking is NOT: no file-path field exists anywhere in the forwarded events, so 'downloaded this document' cannot be expressed. Byte volume is used where the event carries it (about one event in six) and is a secondary signal by design. The serial is met on the frequency wording; the download wording is met only by volume, not by file.
SN 40: Access high-value assets: User starts accessing and downloading high- value assets with increased frequency.
30, 67 | UEBA | Aditya Umathe | SN 30: The solution should be able to automatically identify and classify users and entities (i.e. devices, applications, servers, data, or anything with an IP address) | Can Be | UEBA | 5 | Planned | Aditya | 2026-12-14 | 2026-12-18 | P2 - Any field as an entity, classified automatically. By 31-Jan-2027: any field in the incoming events can be mapped as an entity and scored for anomalies without code changes, and users, devices, applications, servers and addresses are identified and classified automatically. The entity schema already stores a kind-and-value pair, so no data migration is needed. Full estimate 5 d; all done by 31-Jan-2027.
SN 67: Solution should allow users to consider any field as entity and map it for anomaly detection.
45 | UEBA | Aditya Umathe | SN 45: UEBA should activate rules for a set of users until a specified condition or specified time window | Can Be | UEBA | 5 | Planned | Aditya | 2026-12-21 | 2026-12-25 | P2 - Time-bound and condition-bound rules. By 31-Jan-2027: rules and watch lists that apply to a named set of users and switch themselves off on a date or when a stated condition is met. Full estimate 5 d; all done by 31-Jan-2027.
7 | UEBA | Aditya Umathe | SN 7: The solution should have permission for device admin, subnet admin. | Can Be | UEBA | 4 | Planned | Aditya | 2026-11-16 | 2026-11-20 | P1 - Device-admin and subnet-admin permissions. By 31-Jan-2027: scoped administrator roles limited to a named set of devices or to an IP subnet, enforced on every console route. Full estimate 4 d; all done by 31-Jan-2027.
56 | UEBA | Aditya Umathe | SN 56: The solution's UI should allow checking the device summary and similar device behaviour | Can Be | UEBA | 4 | Planned | Aishwarya | 2026-12-14 | 2026-12-18 | P2 - Device summary and similar-device comparison. By 31-Jan-2027: a device summary view, and one device's behaviour compared against devices that behave like it, using the existing similarity index. Full estimate 4 d; all done by 31-Jan-2027.
23 | UEBA | Aditya Umathe | SN 23: Customizable dashboards, configurable policies and risk model optimization | Can Be | UEBA | 6 | Planned | Aditya | 2027-01-25 | 2027-01-29 | P3 - Customizable dashboards and risk-model tuning. By 31-Jan-2027: analysts arrange their own dashboard panels, edit policies from the console, and tune risk-model weights and thresholds without a code change. Full estimate 6 d; all done by 31-Jan-2027.
42 | UEBA | Aditya Umathe | SN 42: Usage deviates from peer group: User pattern of activity starts deviating from the peer group | Can Be | UEBA | 8 | Planned | Aditya | 2026-12-21 | 2027-01-01 | P2 - Peer-group deviation. By 31-Jan-2027: users grouped into cohorts and flagged when their activity pattern drifts from the cohort. Needs department, role and business-unit attributes from OPTCL HR or Active Directory by Day 30 (01-Dec-2026). There is no peer group without them, so if they are late the full 8 d drops out. Full estimate 8 d; all done by 31-Jan-2027. | AT RISK - THERE IS NO PEER GROUP WITHOUT HR DATA. Needs department, role and business-unit attributes for users from OPTCL HR or Active Directory by Day 30 (01-Dec-2026). A cohort cannot be formed without them, so the full 8 days drops out if they do not arrive. Nothing in the engine can substitute for them.
12, 46 | UEBA | Aditya Umathe | SN 12: Ability to monitor, report and alert on the data streaming in and out of the system | Complied - DONE 2026 | UEBA | 0 | Done | Aishwarya | 2026-12-21 | 2027-01-01 | DONE. SN 12: transfer volume is recorded per entity on every event and is reportable and alertable from the console. SN 46: an alert fires when a transfer is both above an absolute floor AND a multiple of what that entity normally moves - both conditions, so neither a chatty host nor a tiny baseline produces noise. NOTE: the earlier 'events carry no volume figures' risk on this row was wrong. Byte counts are present on the forwarded events and were measured before the build started. | AT RISK - THE EVENTS CARRY NO VOLUME FIGURES TODAY. Needs byte counts added to the events the SIEM forwards by Day 35 (06-Dec-2026). Without them we can flag that a transfer looks abnormal but cannot measure how much data actually moved, which is precisely what the requirement asks for.
SN 46: More data being transferred then a normal to and from servers and / or external locations
57 | UEBA | Aditya Umathe | SN 57: The solution's UI should allow using advanced search for detail connection information. Certain application-layer protocols are further decoded during this process | Can Be | UEBA | 6 | Planned | Aditya | 2027-01-25 | 2027-01-29 | P3 - Advanced connection search with application-layer decoding. By 31-Jan-2027: advanced search over detailed connection information, with application-layer protocol fields decoded and searchable. Needs the decoded application-layer fields forwarded by the SIEM team by Day 40 (11-Dec-2026); otherwise protocol decoding stays with the SIEM and the 6 d drops out. Full estimate 6 d; all done by 31-Jan-2027. | AT RISK ON THE SIEM TEAM. Needs decoded application-layer protocol fields forwarded by Day 40 (11-Dec-2026). If they are not, protocol decoding stays with the SIEM and the 6 days drops out. This one sits in the final week, so there is no slack behind it - a late input cannot be absorbed.
43 | UEBA | Aditya Umathe | SN 43: Change in account privileges: User attempts to change privileges on existing account or open new accounts on other systems | Can Be | UEBA | 2 | Planned | Aishwarya | 2027-01-04 | 2027-01-08 | P3 - Change in account privileges. By 31-Jan-2027: detection of attempts to change privileges on an existing account or to open new accounts on other systems. Needs account-management and privilege-change events forwarded by the SIEM team by Day 45 (16-Dec-2026); the work starts once they arrive. Full estimate 2 d; all done by 31-Jan-2027. | BLOCKED ON THE SIEM TEAM - VERIFIED 29-Oct-2026. Sampled 8,094 consecutive events from the live enriched stream plus 3,376 alerts: not one account-management or privilege-CHANGE event is present. No 4720 (account created), no 4728/4732/4756 (group membership added), no 4672 (special privileges assigned), no 4704 (user right assigned), no 4738 (account changed). The word 'account' appears in rule text on 1 event in 8,094. What IS forwarded is privilege USE, not privilege CHANGE: 4673 failed privileged operations and the elevated_process / privilege_escalation rule groups. SN 43 asks specifically for attempts to CHANGE privileges or CREATE accounts, so there is nothing to detect on until the Windows Security account-management channel is forwarded. Needed by Day 45 (16-Dec-2026). The build is 2 days and starts the day those events arrive.
31 | UEBA | Aditya Umathe | SN 31: Support highly available component architecture ensuring no single point of failure | Can Be | UEBA | 22 | Planned (partial only) | Aditya | 2026-11-02 | 2026-12-18 | P1 - Highly available component architecture. By 31-Jan-2027: the full architecture delivered - no single point of failure, clustered datastore in place of single-file storage, leader election so only one engine runs a window, load-balanced console, failover and a documented capacity model (architecture complete 18-Dec-2026). Full estimate 22 d; left after 31-Jan: the 99.9% uptime demonstration. That figure allows about 8.8 hours of downtime a year, so it can only be evidenced by running for months - it is a measurement, not a build task. Also needs the second server from the hardware order. | PARTIAL BY 31-JAN-2027, AND THE LARGEST ITEM ON THE SHEET (22 d). Delivered: the complete architecture by 18-Dec-2026 - clustered datastore in place of single-file storage, leader election, load-balanced console, failover and a documented capacity model. Not delivered: the 99.9% uptime evidence. That figure allows about 8.8 hours of downtime a year, so it can only be demonstrated by running for months - it is a measurement, not a build task. The 22 days are large because the storage layer has to be replaced underneath a running system. Also needs the second server from the hardware order.
44 | UEBA | Aditya Umathe | SN 44: Application misuse by sequence of actions: User performs a sequence of actions which no other user is performing | Can Be | UEBA | 14 | Planned | Aditya, Aishwarya | 2026-12-28 | 2027-01-08 | P2 - Application misuse by sequence of actions. By 31-Jan-2027: sequences of actions modelled per user and scored, so a user performing a sequence no other user performs is flagged, with the verdict fused into the existing risk score. This is a new detection type - the current feature vector is point-in-time only and carries no notion of order. Full estimate 14 d; all done by 31-Jan-2027. | LARGE ITEM (14 d), NO EXTERNAL DEPENDENCY. This is a new detection type rather than a tuning change: the current feature vector is point-in-time only and carries no notion of order, so sequence modelling, scoring and fusion of the verdict into the existing risk score all have to be added. Scheduled across weeks 9-10 with two engineers.
26 | UEBA | Aditya Umathe | SN 26: Support natural language search capability without requiring to learn a custom search query language | Can Be | UEBA | 12 | Planned | Aditya, Aishwarya | 2027-01-04 | 2027-01-15 | P3 - Plain-language search. By 31-Jan-2027: analysts search in ordinary English with no custom query language to learn, translated to the existing search API. Runs fully on the OPTCL host - no external service is called, which keeps SN 64 intact. Full estimate 12 d; all done by 31-Jan-2027. | LARGE ITEM (12 d), NO EXTERNAL DEPENDENCY. Plain-language search must run entirely on the OPTCL host to keep SN 64 intact, so it cannot call any external service. That constraint, plus translating free text onto the existing search API, is where the 12 days go. Scheduled across weeks 10-11 with two engineers.
50, 60, 61 | UEBA | Aditya Umathe | SN 50: Work-centric UI with case management, or input to third-party solutions | Can Be | UEBA | 8 | Planned | Aditya | 2026-11-30 | 2026-12-11 | P2 - Case management. By 31-Jan-2027: a case store with create, assign, status, priority and analyst notes; analysts build an incident from events and alerts; any element - metric graph, log entry, alert - can be correlated into that incident; and the incident exports as a report. Decide before work starts whether cases live in SOAR or in UEBA so they are not built twice. Full estimate 8 d; all done by 31-Jan-2027. | DECISION NEEDED BEFORE WORK STARTS - not an external dependency. Agree whether cases live in SOAR or in UEBA before week 5, otherwise the same case store gets built twice. 8 days either way, but only once.
SN 60: Allows us to create Incidents out of Events/alerts onto which analysts will collaborate inputs and for which, reports can be exported
SN 61: Multiple elements can be correlated into an incident, from metric graphs to device log entries.
Needs more time - 10 d or more, or only partly inside the 90 days
Cannot be done - not a question of time